## Sheet1
SONI TSO Spend and TAO Estimate - 2018 v 2019 TIP
Project 2018 TIP | 2018 TSO cost estimate (£m) | 2018 TO cost estimate (£m) | 2018 Estimated Completion Date | Comment | Project 2019 TIP | 2019 TSO cost estimate (£m) | 2019 CAPEX cost estimate (£m) | 2019 Estimated Completion Date | TSO cost estimate Variance (£m) | TO cost estimate Variance (£m) | Reason for Variance
Tyrone Cavan Interconnector | 13 | 109.3 | 2021 |  | Tyrone Cavan Interconnector | 16.43 | 116.3 | 2023 | 3.43 | 7 | The additional TSO costs are mostly related to the level of stakeholder engagement and technical support that we expect we might need to undertake to secure planning permission as a result of the delays to the approval of planning permission. This is particularly focused on supporting any processes that follow from a ministerial decision.
Airport Road | 0.74 | 7.31 | 2022 |  | Airport Road | 0.98 | 6.8 | 2022 | 0.24 | -0.51 | Small variance resulting from an increase in the TSO workload in response to the complexities that have emerged.
Armagh Main | 0.63 | 21.9 | 2027 |  | Armagh Main | 2.86 | 24.9 | 2027 | 2.23 | 3 | Increase in TSO costs driven by a greater understanding of the likely optimum solution, including the extent of stakeholder engagement that is expected to be required to deliver the necessary consents in a timely way.
East Tyrone Reinforcement | 0.2 |  | 2022 | Project omitted from TDPNI 2018 | East Tyrone Reinforcement | 0.14 | 1.6 | 2022 | -0.06 | 1.6 | TSO costs have increased because the scope of the project has become better understood.
Castlereagh Tx 4 | 0.6 | 8.06 | 2022 |  | Castlereagh Tx 4 | 0.59 | 10.7 | 2022 | -0.01 | 2.64 | The estimated TSO costs included in this TDP have been modified to allow form added complexity associated with the Belfast Power Limited connection. The TSO costs now include an allowance for design and consents to extend the substation.
Ballylumford - Castlereagh | 0.25 | 12.5 | 2022 |  | Ballylumford - Castlereagh |  |  |  | -0.25 | -12.5 | See Ballylumford - Eden, Eden-Carnmoney and Carnmoney - Castlereagh below
Coolkeeragh Tx 110kV cable uprate | 0.01 | 0.54 | 2025 |  | Coolkeeragh Tx 110kV cable uprate | 0.07 | 0.6 | 2021 | 0.06 | 0.06 | TSO costs updated to reflect the scope of works now expected to be required.
NW of NI Reinforcement (110kV restrings) | 0.6 |  | 2025 | Project described but not costed (n/a) | NW of NI Reinforcement (110kV restrings) | [5 empty] | See Strabane - Omagh, Coolkeeragh - Killymallaght, Coolkeeragh - Strabane and Killymallaght - Strabane
Cregagh Tx B sw/gear | 0.02 | 0.29 | 2022 |  | Cregagh Tx B sw/gear | 0.25 | 1.3 | 2022 | 0.23 | 1.01 | Project renamed "Cregagh tx B switchgear and transformer realignment". Proximity outage requires possible substation extension, not foreceen in 2018. Costs updated to reflect the expected workload because the scope of work associated with the expected solution is becoming clearer.
Castlereagh/Knock cables | 0.06 | 1.22 | 2021 |  | Castlereagh/Knock cables | 0.07 | 1.2 | 2021 | 0.01 | -0.02 | TSO cost modified slightly to reflect the expected workload.
Castlereagh and Tandragee 110kV Sw/gear uprating | 0.02 | 7.42 | 2021 |  | Castlereagh and Tandragee 110kV Sw/gear uprating | 0.14 | 7.1 | 2021 | 0.12 | -0.32 | Variance reflects the derating studies and makes provision for specialist consultant studies if required.
Tandragee 2nd bus coupling circuit breaker | 0.02 | 2.14 | 2021 |  | Tandragee 2nd bus coupling circuit breaker | 0.08 | 2.1 | 2021 | 0.06 | -0.04 | TSO costs updated to reflect the expected workload because the scope of work associated with the expected solution is becoming clearer.
Northwest SPS | 0.02 | 0.34 | 2019 |  | Northwest SPS | 0.04 | 0.4 | 2019 | 0.02 | 0.06 | TSO costs updated to reflect the outturn of SONI’s work on the project.
Low Freq load disc. | 0.02 | 0.45 | 2021 |  | Low Freq load disc. | 0.12 | 0.9 | 2022 | 0.1 | 0.45 | TSO costs updated to reflect the expected scope of work required to deliver this project.
Castlereagh reactors | 0.05 | 0.27 | 2024 |  | Castlereagh reactors | 0.11 | 3.6 | 2022 | 0.06 | 3.33 | Project renamed "Castlereagh, Tandragee and Hannahstown reactors", as project became better understood. Variance reflected the design feasibility.
Voltage support - Coleraine | 1 | 21.4 | 2021 |  | Voltage support - Coleraine |  |  |  | -1 | -21.4 | Project Cancelled
Voltage support - Omagh | 1.1 | 23.3 | 2021 |  | Voltage support - Omagh |  |  |  | -1.1 | -23.3 | Project Cancelled
Voltage support - Tamnamore | 1.1 | 23.3 | 2021 |  | Voltage support - Tamnamore |  |  |  | -1.1 | -23.3 | Project Cancelled
Creagh/Kells - Rasharkin 110kV cct | 1.41 | 23.07 | 2024 |  | Creagh/Kells - Rasharkin 110kV cct | 1.76 | 21.8 | 2026 | 0.35 | -1.27 | Small increase in TSO costs to reflect the expected scope of the work required to deliver this project.
Omagh - Dromore uprating | 0.06 | 3.25 | 2019 |  | Omagh - Dromore uprating | 0.16 | 4.4 | 2022 | 0.1 | 1.15 | Varaiance reflects feasibility studies and possible CLUD
Turleenan /Tamanmore 275kV uprating | 0.15 | 2.28 | 2022 |  | Turleenan /Tamanmore 275kV uprating | 0.29 | 4.3 | 2022 | 0.14 | 2.02 | Varaiance reflects complexity of feasibility studies and possible CLUD given experience from Omagh - Dromore project
Turleenan - Dromore/Donegal 275kV | 5.43 | 160 | 2025 | TDPNI 2018 appears to state £170m, however this should be £160m | Turleenan - Dromore/Donegal 275kV | 4.5 | 170 | 2026 | -0.93 | 10 | Project renamed "North West of NI large scale reinforcement". TSO costs updated to reflect the complex suite of potential solutions to this need and to deliver the engagement necessary to secure the consents for this suite of solutions in a timely manner. The updated TAO costs reflect the current estimate of the likely infrastructure required.
Coolkeeragh / Trillick 110kV cct | 0.55 | 8.5 | 2025 |  | Coolkeeragh / Trillick 110kV cct | 0.85 | 8.9 | 2025 | 0.3 | 0.4 | The TSO cost shave been updated to reflect the additional work that would be required by the TSO to deliver the solution that we currently expect to be the optimum outcome. The scheme currently expected to be the optimum is a solution with a lower capital cost that that previously assumed.
Augmentation of capacity at 110kV interface | 1.2 | 13.6 | 2022 |  | Augmentation of capacity at 110kV interface |  | 3 | 2025 | -1.2 | -10.6 | This project has been split into Gort 2nd Tx, Rasharkin 2nd Tx and the afforementioned "Augmentation of capacity at 110kV interface". The remaining TAO estimate is for possible works at Omagh, Coleraine, Limavady and Strabane. This project will be better understood in time and future versions of the TDPNI will clarify this.
TOTAL | 28.24 | 450.44
Rescoped Projects
[5 empty] | Gort 2nd Tx | 0.15 | 1.5 | 2022 | 0.15 | 1.5 | This is a new project.
[5 empty] | Rasharkin 2nd Tx | 0.15 | 1.7 | 2022 | 0.15 | 1.7 | This is a new project.
[5 empty] | Ballylumford Eden | 0.48 | 9.5 | 2022 | 0.48 | 9.5 | The TSO costs are updated to reflect the expected needs of the scheme (includes asset replacement element
[5 empty] | Castlereagh - Carnmoney | 2.51 | 28.5 | 2024 | 2.51 | 28.5 | The complexity associated with theTSO tasks to deliver the likely solution to this need have become better understood over the past year. Major consultation exercises are expected to be required due to OHL recovery, cable routes and substations taking place in urban areas
[5 empty] | Eden - Carnmoney | 0.86 | 7.9 | 2023 | 0.86 | 7.9 | TSO costs updated to reflect the complexity of the expected solution and need for appropriate stakeholder engagement.
[5 empty] | Strabane Omagh | 0.5 | 5 | 2026 | 0.5 | 5 | Cost estimate for permitted development checks and feasibility studies to confirm optimum solution.
[5 empty] | Strabane - Killymallaght |  |  | 2028 |  |  | Cost still be defined
[5 empty] | Coolkeeragh - Killymallaght |  |  | 2028 |  |  | Cost still be defined
[5 empty] | Coolkeeragh - Strabane |  |  | 2028 |  |  | Cost still be defined
[5 empty] | NW reinforcement (110kV) | 2.27 | 30 | 2026 | 2.27 | 30 | TSO costs updated to reflect learning from recent work in the study area and to ensure that appropriate investigations and stakeholder engagement are undertaken.
New Projects
[5 empty] | Moyle 275kV reinforcement | 0.58 | 4.1 | 2028 | 0.58 | 4.1 | This is a new project.
[5 empty] | CVT PQ | 0.07 | 1.1 | 2022 | 0.07 | 1.1 | TSO costs updated to reflect the expected scope of work required to deliver this project.
[5 empty] | Coolkeeragh - Magherafelt HSAR (High Speed Auto Reclose)/SPT (Single Phase Tripping) | 0.12 | 2.12 | 2024 | 0.12 | 2.12 | This is a new project.
[5 empty] | Filter tuning or new filters | 0.24 | 2.2 | 2025 | 0.24 | 2.2 | This is a new project.
[5 empty] | Omagh - Dromore third cct | 1.54 |  | 2028 | 1.54 |  | This is a new project and costs are still to be defined
[5 empty] | Drumnakelly - Tamnamore restring | 0.17 |  | 2027 | 0.17 |  | This is a new project and costs are still to be defined
[5 empty] | 22kv switchgear | 0.07 | 2.1 | 2024 | 0.07 | 2.1 | This is a new project.
[5 empty] | Voltage support Coolkeeragh | 0.87 | 20.87 | 2023 | 0.87 | 20.87 | TSO costs reflect current understanding of the works required to deliver the expected solution.
[5 empty] | Unspecified | 1.74 |  |  | 1.74 |  | This project is a placeholder for the work that we expect to emerge to achieve new targets for renewable electricity. This includes assumptions about the extent of stakeholder engagement required and the type of solutions that will emerge. This project is not specified in TDPNI 2019
[5 empty] | Trialling new technologies | 0.19 |  |  | 0.19 |  | This is a new project and is not specified in TDPNI 2019
[5 empty] | TOTAL | 41.95 | 506.49
[5 empty] | TO Total cost = (Capex - TSO cost) |  | 464.54