## Annex G Nominated Outputs 03.00
Annex G - Nominated outputs list
A |  |  |  |  | B
Project Information |  |  |  |  | Project Outputs
Project ID Reference | Project Name | PC21 Programme | Quality Regulator Date (if appropriate) | Current Actual or Projected Beneficial use date (if appropriate) | PC21 Output Ref Code | Output Units | PC10 | PC10 | PC10 | PC13 | PC15 | PC15 | [5 empty] | PC21
PI_Project_ID | PI_Project_Name | PI_PC21_Prog |  | CAM_BU |  |  | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Water Treatment Base Maintenance
JA271 | Killylane WTW | 1 |  | 2014-12-31 | 7 | nr | bar: PC15 2014-15
Water Treatment Works
JN390 | Lough Bradan WTWs Upgrade | 4 |  | 2011-03-02 | 7 | nr | bar: PC10 2010-11
JL723 | Carmoney Water Treatment Works Upgrade | 4 |  | 2011-03-30 | 7 | nr | bar: PC10 2010-11
JP669 | Killyhevlin WTW - Enforcement Order | 4 |  | 2015-03-31 | 7 | nr | bar: PC15 2014-15
JR463 | Dorisland WTW GAC plant | 4 |  | 2015-03-27 | 7 | nr | bar: PC15 2014-15
JI052 | Glenhordial Treatability | 4 |  | 2016-01-29 | 7 | nr | bar: PC15 2015-16
JI052 | Dorisland Treatability | 4 |  | 2021-03-31 | 7 | nr | bar: PC15 2020-21
JI052 | Killyhelvin Treatability | 4 |  | 2021-03-31 | 7 | nr | bar: PC15 2020-21
JC390 | Rathlin Island Borehole | 4 |  | 2020-12-31 | 7 | nr | bar: PC15 2019-20
JL795 | Ballinrees WTW, MCPA treatment investigations | 4 |  | 2024-03-31 | 7 | nr | PC15 2020-21: 0; PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
JN538 | Derg WTW MCPA PEO Undertakings | 4 |  | 2020-08-31 | 7 | nr | PC15 2020-21: 0; PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1116 | Glenhordial Treatability Improvements | 04a |  | 2027-03-16 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1927 | Derg Treatability Improvements | 04a |  | 2025-03-28 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1117 | Lough Bradan Treatability Improvements | 04a |  | 2027-03-16 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1111 | Lough Fea Treatability Improvements | 04a |  | 2024-02-07 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2016 | Glenhordial WTW Sludge Improvements | 04a |  | 2024-03-26 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1115 | Belleek Treatability Improvements | 04a |  | 2023-10-05 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1118 | Seagahan Treatability Improvements | 04a |  | 2027-01-06 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1050 | Loughmacrory Treatability Improvements | 04a |  | 2027-03-31 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1073 | Upgrade to Killyhevlin | 04a |  | 2027-03-16 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1907 | Carmoney Treatability Improvements | 04a |  | 2024-04-03 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2020 | Caugh Hill Treatability Improvements | 04a |  | 2024-05-13 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1113 | Carran Hill Treatability Improvements | 04a |  | 2023-10-05 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1112 | Fofanny Treatability Improvements | 04a |  | 2027-03-16 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1668 | NIW Alpha WTWs Treatability Improvements | 04a |  | 2027-01-01 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1084 | Clay Lake Treatability Improvements | 04a |  | 2026-03-17 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1695 | Killyhevlin DWW Tank | 04a |  | 2027-03-16 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1550 | Dungonnell Treatability Improvements | 04a |  | 2022-03-23 | 7 | Nr | PC21 2021-22: 1; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1664 | Drumaroad Treatability Improvements | 04a |  | 2023-05-11 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1186 | Altnahinch Treatability Improvements | 04a |  | 2025-04-07 | 7 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
Trunk Mains
JR416 | CTM Extension - Barnetts Park to Purdysburn | 5 |  | 2010-11-29 | 6 | nr | bar: PC10 2010-11
JG036 | Castor Bay to Dungannon Strategic Trunk Mains | 5 |  | 2011-05-24 | 6 | nr | bar: PC10 2010-11
JG035 | Ballydougan to Newry Main Link Reinforcement Phase 1 | 5 |  | 2012-12-04 | 6 | nr | bar: PC10 2012-13
JG035 | Ballydougan to Newry TM - Phase 2A | 5 |  | 2012-12-17 | 6 | nr | bar: PC10 2012-13
JR460 | Gravity II McVeighs Well to Oldpark SR | 5 |  | 2014-11-30 | 6 | nr | bar: PC15 2014-15
JG035 | Ballydougan to Newry TM - Phase 2B | 5 |  | 2016-03-31 | 6 | nr | bar: PC15 2015-16
JR342 | Castor Bay to Belfast TM | 5 |  | 2015-05-08 | 6 | nr | bar: PC15 2015-16
JB693 | Carland to Cookstown Trunkmain | 5 |  | 2017-03-31 | 6 | nr | bar: PC15 2016-17
2550 | Trunkmain - Killyhevlin Cavanacross B | 05a |  | 2025-02-28 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2047 | Edenasop to Killeter SR | 05a |  | 2025-03-31 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2498 | Castor Bay Outage September 2019 | 05b |  | 2027-01-31 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2050 | Woodend to Drain main | 05a |  | 2024-05-09 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2610 | Trunkmain - Whitespots B | 05a |  | 2023-03-31 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1729 | Trunkmain - Crescent Link | 05c |  | 2023-07-18 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1804 | Trunkmain - Skeoge Link | 05c |  | 2025-09-30 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1784 | Trunkmain - High Tober | 05a |  | 2027-03-30 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2513 | Castor Bay to Ballydougan Trunk Main September 2019 | 05a |  | 2025-03-31 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2048 | Blacklough to Crocknabohill SR | 05a |  | 2027-01-31 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2507 | Central WRZ Resilience and Supply | 05b |  | 2025-04-16 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1245 | Western Resource Zone - Resilience | 05b |  | 2025-01-10 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
JL790 | Northern WRZ Resilience | 05b |  | 2022-05-27 | 6 | Nr | PC15 2020-21: 1; PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
JL715 | Caugh Hill, Carmoney to Strabane Strategic Link Watermain | 05a |  | 2026-05-04 | 6 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
Service Reservoirs & Clear Water Tanks
JB665 | Tullaghans SR, Dunloy, New Reservoir | 6 |  | 2010-08-13 | 8 | nr | bar: PC10 2010-11
JC381 | Altnahinch WTP, Ballymoney, New CWB. | 6 |  | 2010-11-10 | 8 | nr | bar: PC10 2010-11
JC378 | Glenlough SR, Ballymoney, New SR | 6 |  | 2010-12-20 | 8 | nr | bar: PC10 2010-11
JR151 | West Belfast/ North Lisburn (Crew Hill) | 6 |  | 2011-01-18 | 8 | nr | bar: PC10 2010-11
JB648 | Dungonnell Command Service Reservoir | 6 |  | 2011-03-31 | 8 | nr | bar: PC10 2010-11
JF583 | Carland Service Reservoir | 6 |  | 2011-04-11 | 8 | nr | bar: PC10 2011-12
JS179 | Ballykine Gravity Distribution | 6 |  | 2011-04-20 | 8 | nr | bar: PC10 2011-12
JV827 | Tullyhappy SR | 6 |  | 2011-12-09 | 8 | nr | bar: PC10 2011-12
JB649 | Tully SR | 6 |  | 2012-12-06 | 8 | nr | bar: PC10 2012-13
JV830 | Crieve SR | 6 |  | 2015-03-27 | 8 | nr | bar: PC15 2014-15
JP631 | Killyhelvin Clear Water Tank | 6 |  | 2020-05-31 | 8 | nr | bar: PC15 2020-21
JB709 | Lough Fea CWB | 6 |  | 2020-03-31 | 8 | nr | bar: PC15 2019-20
JC385 | Monaclogh SR | 6 |  | 2017-08-01 | 8 | nr | bar: PC15 2017-18
1546 | SR - Loughmacrory Hill | 06z |  | 2025-10-31 | 8 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1640 | CWT - Fofanny | 06z |  | 2025-10-30 | 8 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1642 | CWT - Seagahan | 06z |  | 2026-03-23 | 8 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
JS274 | Drumaroad WTW Clear Water Tank | 06z |  | 2021-08-25 | 8 | Nr | PC21 2021-22: 1; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
Unsatisfactory Intermittent Discharges
KA247 | UID387 Crumlin Town WWPS Upgrade | 12 |  | 2020-03-01 | 12 | nr | bar: PC15 2019-20
KA248 | UID190 Brustin Lee WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KA248 | UID319 Croft Manor WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KA248 | UID320 Ballygalley Slipway WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KA248 | UID321 Ballygalley North WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KA248 | UID322 Ballygalley Coast Road CSO | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KA251 | UID394 Clotworthy House CSO | 12 |  | 2014-01-22 | 12 | nr | bar: PC13 2013-14
KA252 | UID398 Glynn WWPS | 12 |  | 2015-02-19 | 12 | nr | bar: PC15 2014-15
KA260 | UID389 Muckamore WwPS | 12 |  | 2017-04-04 | 12 | nr | bar: PC15 2017-18
KA261 | UID388 Milltown Road WWPS Upgrade | 12 |  | 2017-03-21 | 12 | nr | bar: PC15 2016-17
KA262 | UID391 Islandreagh WWPS Upgrade | 12 |  | 2019-03-30 | 12 | nr | bar: PC15 2020-21
KA263 | UID390 Dunadry WWPS Upgrade | 12 |  | 2019-03-30 | 12 | nr | bar: PC15 2020-21
KB486 | UID399 Galgorm Raphael WWPS | 12 |  | 2018-03-20 | 12 | nr | bar: PC15 2018-19
KC415 | UID043 Screen Road CSO | 12 |  | 2015-03-30 | 12 | nr | PC15 2014-15: 1; PC15 2015-16: 0
KC415 | UID040 Ballysally CSO | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KF037 | UID245 Annagher SPS | 12 |  | 2014-03-28 | 12 | nr | bar: PC13 2013-14
KF037 | UID246 Campbells Garage WwPS CSO | 12 |  | 2014-03-28 | 12 | nr | bar: PC13 2013-14
KF037 | UID247 Washing bay Road WwPS CSO | 12 |  | 2014-03-28 | 12 | nr | bar: PC13 2013-14
KF330 | UID001 Scotch Street CSO. 2 | 12 |  | 2016-03-25 | 12 | nr | bar: PC15 2015-16
KF330 | UID002 Scotch Street. CSO 1 | 12 |  | 2016-03-25 | 12 | nr | bar: PC15 2015-16
KF330 | UID003 Courthouse 1 CSO | 12 |  | 2015-11-30 | 12 | nr | bar: PC15 2015-16
KF330 | UID005 The Mall East CSO | 12 |  | 2016-10-14 | 12 | nr | bar: PC15 2016-17
KF330 | UID006 English St CSO. Scheme 2 | 12 |  | 2017-01-21 | 12 | nr | bar: PC15 2016-17
KF330 | UID007 Drumcairn SPS. Scheme 3 | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KF330 | UID431 Ballycrummy WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KF330 | UID430 Longstone WWPS | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KF330 | UID010 Newry Road SPS | 12 |  | 2017-04-28 | 12 | nr | bar: PC15 2017-18
KF330 | UID173 Mall West CSO | 12 |  | 2016-03-23 | 12 | nr | bar: PC15 2015-16
KF330 | UID175 Alexender Road CSO | 12 |  | 2015-11-13 | 12 | nr | bar: PC15 2015-16
KF330 | UID176 Gillis Lane CSO | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KF354 | UID416 Dernagh WWPS | 12 |  | 2014-09-01 | 12 | nr | bar: PC15 2014-15
KF360 | UID418 Blackwatertown WWPS | 12 |  | 2014-03-31 | 12 | nr | bar: PC13 2013-14
KI488 | UID400 Braeside WWPS | 12 |  | 2013-08-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID401 Cloughy Road WWPS | 12 |  | 2013-09-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID402 Old Mill Race WWPS | 12 |  | 2013-08-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID403 Glen Park WWPS | 12 |  | 2013-09-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID404 Kerries Glen | 12 |  | 2014-01-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID405 Carnesure Terrace WWPS | 12 |  | 2014-04-01 | 12 | nr | bar: PC15 2014-15
KI488 | UID406 Hillside WWPS | 12 |  | 2013-10-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID407 Chimera Wood WWPS | 12 |  | 2013-12-01 | 12 | nr | bar: PC13 2013-14
KI488 | UID408 Ballystockart WWPS | 12 |  | 2014-11-01 | 12 | nr | bar: PC15 2014-15
KI488 | UID409 Milltown WWPS | 12 |  | 2014-10-01 | 12 | nr | bar: PC15 2014-15
KI488 | UID419 Ratalla WWPS | 12 |  | 2013-04-01 | 12 | nr | bar: PC13 2013-14
KL468 | UID114 Caw Park CSO 023 | 12 |  | 2016-03-21 | 12 | nr | bar: PC15 2015-16
KL468 | UID380 Gransha Park WwPS No. 2 | 12 |  | 2016-03-22 | 12 | nr | bar: PC15 2015-16
KL504 | UID273 Knockalla New WWPS | 12 |  | 2016-09-13 | 12 | nr | bar: PC15 2016-17
KL504 | UID274 Upper Galliagh Road WWPS | 12 |  | 2016-03-31 | 12 | nr | bar: PC15 2015-16
KL504 | UID275 Glen Road CSO | 12 |  | 2015-04-24 | 12 | nr | bar: PC15 2015-16
KL504 | UID433 Fairview Knockalla CSO | 12 |  | 2016-03-21 | 12 | nr | bar: PC15 2015-16
KL524 | UID420 Bleachgreen WWPS | 12 |  | 60/06/2017 | 12 | nr | bar: PC15 2017-18
KL527 | UID432 Manorwood WWPS | 12 |  | 2016-12-01 | 12 | nr | bar: PC15 2016-17
KN628 | UID427 Carrickmore WWPS | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KN644 | UID417 Greenbridge WWPS | 12 |  | 2013-11-14 | 12 | nr | bar: PC13 2013-14
KR417 | UID191 Cromac Street CSO 95 | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2018-19
KR417 | UID192 Outside Holiday Inn CSO97 | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2018-19
KR417 | UID193 Dublin Road Cinema CSO 96 | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2018-19
KR417 | UID194 Bankmore Street / Dublin Road CSO 81 | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2018-19
KR417 | UID265 Sandy Row CSO 94 | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2018-19
KR480 | UID218 Palace Barracks CSO 110 | 12 |  | 2016-09-07 | 12 | nr | bar: PC15 2016-17
KR480 | UID219 Jackson Road CSO 52 | 12 |  | 2014-10-06 | 12 | nr | bar: PC15 2014-15
KR501 | UID272 Carrickfergus CSO | 12 |  | 2015-03-19 | 12 | nr | bar: PC15 2014-15
KR504 | UID351 Portaferry Road WWPS | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2019-20
KR640 | UID220 Strathearn Court CSO 53 | 12 |  | 2016-12-20 | 12 | nr | bar: PC15 2016-17
KS372 | UID044 Market Street SPS Upgrade, Downpatrick - UID's | 12 |  | 2016-02-18 | 12 | nr | bar: PC15 2015-16
KS373 | UID046 Meadowlands CSO3 | 12 |  | 2013-05-06 | 12 | nr | bar: PC13 2013-14
KS373 | UID047 Church Street CSO1 | 12 |  | 2013-05-06 | 12 | nr | bar: PC13 2013-14
KS373 | UID048 Scotch Street CSO4 | 12 |  | 2013-05-06 | 12 | nr | bar: PC13 2013-14
KS373 | UID049 Scotch Street CSO11 | 12 |  | 2013-05-06 | 12 | nr | bar: PC13 2013-14
KS373 | UID050 Rathkeltair Terr CSO12 | 12 |  | 2013-05-06 | 12 | nr | bar: PC13 2013-14
KS374 | UID045 Downpatrick - Stream St CSO | 12 |  | 2015-02-19 | 12 | nr | bar: PC15 2014-15
KS374 | UID124 Hunters Mill Attenuation Stream Street CSO2 | 12 |  | 2015-02-19 | 12 | nr | bar: PC15 2014-15
KS848 | UID 260 Harbour WwPS | 12 |  | 2013-12-09 | 12 | nr | bar: PC13 2013-14
KS867 | UID343 Copeland Road CSO 61 | 12 |  | 2014-10-30 | 12 | nr | bar: PC15 2014-15
KS875 | UID189 Bangor DAP Works Package 6: Lukes Point WWPS UIDs | 12 |  | 2014-09-30 | 12 | nr | bar: PC15 2014-15
KS877 | UID023 Castle Park CSO 07 | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID179 13 Rugby Avenue CS0 8A | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID180 11 Brunswick Road CSO 8B | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID181 104 Abbey Street CSO 8F | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID182 114 Abbey Street CSO 8E | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID183 Railway View Street CSO 8G (not required) | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID184 Abbey Park CSO 9 | 12 |  | 2018-03-31 | 12 | nr | bar: PC15 2017-18
KS877 | UID263 57 Belfast Road CSO 8C | 12 |  | 2017-03-21 | 12 | nr | bar: PC15 2016-17
KS877 | UID264 17 Belfast CSO 8D | 12 |  | 2017-03-21 | 12 | nr | bar: PC15 2016-17
KS879 | UID018 Somerset Ave. CSO 11 | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KS879 | UID019 Bridge St CSO 13 | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KS879 | UID020 Quay St CSO 14 | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KS879 | UID021 Tennyson CSO 10 | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KS879 | UID022 Queens parade CSO 12 | 12 |  | 2014-08-27 | 12 | nr | bar: PC15 2014-15
KS900 | UID410 Glencraig WWPS | 12 |  | 2014-05-01 | 12 | nr | bar: PC15 2014-15
KS903 | UID266 Halfway House CSO | 12 |  | 2016-03-21 | 12 | nr | bar: PC15 2015-16
KS903 | UID267 Marine Park CSO | 12 |  | 2016-03-21 | 12 | nr | bar: PC15 2015-16
KS930 | UID076 Millisle SPS CSO 02 | 12 |  | 2018-12-12 | 12 | nr | bar: PC15 2020-21
KS937 | UID032 Annesborough Park WwPS | 12 |  | 2016-06-30 | 12 | nr | bar: PC15 2016-17
KS939 | UID259 Pattons Bridge (Blackrock WwPS | 12 |  | 2016-03-24 | 12 | nr | bar: PC15 2015-16
KS958 | UID185 Avonlea Park CSO 6 | 12 |  | 2016-03-30 | 12 | nr | bar: PC15 2015-16
KS958 | UID186 Rosemary Crescent / Inglewood Pk CSO 5 | 12 |  | 2016-03-30 | 12 | nr | bar: PC15 2015-16
KS958 | UID187 Clandeboye Road CSO 5B | 12 |  | 2016-03-30 | 12 | nr | bar: PC15 2015-16
KT114 | UID071 Magherageery PS CSO 18 | 12 |  | 2014-03-18 | 12 | nr | bar: PC13 2013-14
KT139 | UID276 River Road WWPS | 12 |  | 2014-04-09 | 12 | nr | bar: PC15 2014-15
KT391 | UID066 Waterside 2 CSO 07 | 12 |  | 2015-03-12 | 12 | nr | bar: PC15 2014-15
KT391 | UID067 B Hilden PS CSO 13B | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KT391 | UID068 Hilden PS CSO 13A | 12 |  | 2015-10-15 | 12 | nr | bar: PC15 2015-16
KT391 | UID069 Antrim St CSO 25 | 12 |  | 2016-08-22 | 12 | nr | bar: PC15 2016-17
KT391 | UID074 Laws Yard CSO 14 | 12 |  | 2015-10-30 | 12 | nr | bar: PC15 2015-16
KT391 | UID221 Waterside 1 CSO 01 | 12 |  | 2015-03-12 | 12 | nr | bar: PC15 2014-15
KT391 | UID222 Linenhall Street CSO 03 | 12 |  | 2015-03-30 | 12 | nr | PC15 2014-15: 1; PC15 2015-16: 0
KT391 | UID223 Antrim Street CSO 05 | 12 |  | 2019-06-30 | 12 | nr | bar: PC15 2018-19
KT391 | UID224 Clonevin Park CSO 10 | 12 |  | 2015-09-09 | 12 | nr | bar: PC15 2015-16
KT391 | UID225 Sprucefield WWPS Screen CSO 20 | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KT391 | UID226 Antrim Road CSO 24 + flooding | 12 |  | 2015-10-30 | 12 | nr | bar: PC15 2015-16
KT391 | UID227 Bow Street CSO 26 | 12 |  | 2016-03-22 | 12 | nr | bar: PC15 2015-16
KT391 | UID228 Ballynahinch Rd 2 CSO 27 | 12 |  | 2015-03-18 | 12 | nr | bar: PC15 2014-15
KT391 | UID229 Grand Street Screen CSO 28 | 12 |  | 2015-11-20 | 12 | nr | bar: PC15 2015-16
KT391 | UID423 Eglantine WWPS CSO 16 | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KT391 | UID424 Culcavy WWPS CSO 17 | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KT391 | UID425 Ballinderry WWPS CSO 23 | 12 |  | 2015-03-30 | 12 | nr | bar: PC15 2014-15
KT391 | UID421 Edgewater WWPS | 12 |  | 2015-09-04 | 12 | nr | bar: PC15 2015-16
KT391 | UID422 Hoggs Weir CSO 04 | 12 |  | 2015-10-30 | 12 | nr | bar: PC15 2015-16
KT403 | UID070 Maralin Ave CSO 02 | 12 |  | 2014-09-30 | 12 | nr | bar: PC15 2014-15
KT415 | UID065 Glenmore SPS CSO 22 | 12 |  | 2013-06-25 | 12 | nr | bar: PC13 2013-14
KV154 | UID095 Newry Road TPS CSO | 12 |  | 2014-01-14 | 12 | nr | bar: PC13 2013-14
KV154 | UID234 Drumsesk Road Header Tank CSO | 12 |  | 2014-01-14 | 12 | nr | bar: PC13 2013-14
KV161 | UID033 Mill Hill CSO 04 | 12 |  | 2014-03-31 | 12 | nr | bar: PC13 2013-14
KV161 | UID031 Ballylough CSO 04 | 12 |  | 2014-03-31 | 12 | nr | bar: PC13 2013-14
KV161 | UID036 Annesborough Park CSO 01 | 12 |  | 2014-03-31 | 12 | nr | bar: PC13 2013-14
KA201 | Ballyeaston, Sewerage System Upgrade | 12 |  | 2012-04-23 | 12 | nr | bar: PC10 2011-12
KA247 | Crumlin Town WWPS Upgrade | 12 |  |  | 12 | nr
KA248 | Ballygally Sewer Rehabilitation | 12 |  |  | 12 | nr
KA251 | Umry Lodge CSO | 12 |  |  | 12 | nr
KA252 | Glynn WWPS | 12 |  |  | 12 | nr
KA260 | Muckamore WWPS Upgrade | 12 |  |  | 12 | nr
KA261 | Milltown Road WWPS Upgrade | 12 |  |  | 12 | nr
KA262 | Islandreagh WWPS Upgrade | 12 |  |  | 12 | nr
KA263 | Dunadry WWPS Upgrade | 12 |  |  | 12 | nr
KB428 | Draperstown DAP | 12 |  | 2010-07-02 | 12 | nr | PC10 2010-11: 2
KB486 | Galgorm WWPS Upgrade | 12 |  |  | 12 | nr
KC404 | Coleraine DAP Phase 1 - UID's | 12 |  | 2012-01-31 | 12 | nr | PC10 2011-12: 5
KC415 | Coleraine | 12 |  |  | 12 | nr
KF037 | Annagher Sewage Pumping Station and Rising Main - UID's | 12 |  |  | 12 | nr
KF330 | Armagh DAP Stage 1 - UID's | 12 |  |  | 12 | nr
KF354 | Dernagh WWPS Upgrade | 12 |  |  | 12 | nr
KF360 | Blackwater Town WWPS Upgrade | 12 |  |  | 12 | nr
KF396 | UID008 Milford SPS | 12 |  | 2017-08-04 | 12 | nr | bar: PC15 2017-18
KF397 | UID009 Killylea SPS | 12 |  | 2020-03-31 | 12 | nr | bar: PC15 2019-20
KG153 | Gilford Road, Portadown, Sewerage Upgrades | 12 |  | 2010-08-10 | 12 | nr | PC10 2010-11: 3
KG178 | Annaghanoon Road WWPS, Waringstown | 12 |  | 2011-09-05 | 12 | nr | bar: PC10 2012-13
KG184 | Portadown Drainage Area Network Improvements - Obins Street and Park Road - UID's | 12 |  | 2012-08-31 | 12 | nr | PC10 2012-13: 4
KI488 | Removal of Inlet Screens and Installation of Solid Handling Pumps | 12 |  |  | 12 | nr
KL428 | Londonderry Sewer Imps Stage 2 - Duke St PS Group Schemes - UID's | 12 |  | 2011-03-28 | 12 | nr | PC10 2010-11: 3
KL443 | Londonderry DAP Duke Street Work Package - UID's | 12 |  | 2011-12-02 | 12 | nr | PC10 2011-12: 4
KL444 | Londonderry DAP, Buncrana Road, Work Package Stage 1- UID's | 12 |  | 2012-05-07 | 12 | nr | PC10 2012-13: 2
KL445 | Londonderry DAP: Victoria road Work Package - UID's | 12 |  | 2010-10-11 | 12 | nr | bar: PC10 2010-11; PC10 2012-13
KL446 | Londonderry DAP, Duke Street Work Package, Flood Alleviation | 12 |  | 2011-12-13 | 12 | nr | PC10 2011-12: 3
KL447 | Londonderry DAP: Foyle Road Work Package: CSO Rationalisation - UID's | 12 |  | 2012-09-24 | 12 | nr | PC10 2012-13: 10
KL448 | Londonderry DAP : Victoria Road Work Package : CSO Rationalisation | 12 |  | 2010-10-29 | 12 | nr | PC10 2010-11: 3
KL449 | Londonderry DAP : Strathfoyle & Drmahoe Work Package : Drumahoe Old WWPS | 12 |  | 2010-09-02 | 12 | nr | bar: PC10 2010-11
KL450 | Londonderry DAP : Strathfoyle & Drmahoe Work Package : Caw WWPS | 12 |  | 2010-07-01 | 12 | nr | bar: PC10 2010-11
KL451 | Londonderry DAP, Strathfoyle + Drumahoe Package: CSO Abandonments - UID's | 12 |  | 2012-09-24 | 12 | nr | PC10 2012-13: 3
KL468 | Strathfoyle, Londonderry Syphon Inlet Screen | 12 |  |  | 12 | nr
KL504 | Londonderry DAP : Buncrana Road Work Package, Stage 2 | 12 |  |  | 12 | nr
KL524 | Bleachgreen WWPS, Londonderry, Upgrade/Replacement | 12 |  |  | 12 | nr
KL527 | Manorwood WWPS Replacement | 12 |  |  | 12 | nr
KN595 | Brookmount Road, Hunters Cresent, Omagh | 12 |  | 2011-05-31 | 12 | nr | PC10 2012-13: 5
KN628 | Carrickmore WWPS Upgrade | 12 |  |  | 12 | nr
KN644 | Greenbridge WWPS Upgrade | 12 |  |  | 12 | nr
KN646 | Winters Lane, CSO Upgrade - UID | 12 |  | 2013-03-27 | 12 | nr | bar: PC10 2012-13
KR400 | Lukes Point DAP Phase 1 | 12 |  | 2010-06-23 | 12 | nr | bar: PC10 2010-11
KR402 | Joymount WWPS | 12 |  | 2010-06-01 | 12 | nr | bar: PC10 2010-11
KR403 | Whitehouse DAP Phase 1 | 12 |  | 2010-04-13 | 12 | nr | PC10 2010-11: 3
KR417 | Ormeau Avenue Sewer investigation and feasibility study for pollution resolution - UID's | 12 |  |  | 12 | nr
KR432 | Beechmount Avenue/Gortfin Street Belfast Hydraulic Upgrade. - UID's | 12 |  | 2011-12-02 | 12 | nr | PC10 2011-12: 4
KR434 | Annadale Flats, Belast | 12 |  | 2012-03-30 | 12 | nr | PC10 2011-12: 4
KR439 | Millisle DAP 1 | 12 |  | 2012-11-29 | 12 | nr | bar: PC10 2012-13
KR440 | Ballywalter DAP Phase 1 | 12 |  | 2010-09-30 | 12 | nr | bar: PC10 2010-11
KR441 | Montgomery Rd, Flood Alleviation - UID's | 12 |  | 2012-04-27 | 12 | nr | PC10 2011-12: 4
KR452 | Baroda Street/Ormeau Park, Belfast CSO | 12 |  | 2011-09-07 | 12 | nr | PC10 2011-12: 2
KR480 | Holywood Sewer Catchment Investigations - UIDs | 12 |  |  | 12 | nr
KR488 | Linen Gardens Belfast CSO Screening - UID's | 12 |  | 2014-01-01 | 12 | nr | bar: PC13 2013-14
KR501 | Carrickfergus WWTW Upgrade | 12 |  |  | 12 | nr
KR504 | Portaferry Road, N,Ards WWPS Upgrade | 12 |  |  | 12 | nr
KR640 | Holywood Sewer Network Improvements- Phase 2 | 12 |  |  | 12 | nr
KS372 | Market Street SPS Upgrade, Downpatrick - UID's | 12 |  |  | 12 | nr
KS373 | Church Street, SPS Upgrade, Downpatrick - UID's | 12 |  | 2013-05-06 | 12 | nr
KS374 | Hunter's Mill Storm Attenuation and Network Improvements | 12 |  |  | 12 | nr
KS377 | Downs Road/Castle Park Sewer Upgrade/ Attenuation - UID's | 12 |  | 2012-01-23 | 12 | nr | PC10 2011-12: 4
KS379 | Murlough SPS Upgrade & Network Improvements - UID's | 12 |  | 2011-04-29 | 12 | nr | PC10 2011-12: 8; PC10 2012-13: 1
KS807 | Kilkeel Harbour SPS and Sewerage Improvements - UID's | 12 |  | 2012-06-04 | 12 | nr | PC10 2012-13: 2
KS812 | Greyabbey DAP Phase 1 - UID's | 12 |  | 2012-09-24 | 12 | nr | PC10 2012-13: 2
KS835 | South Street Newtownards WWPS Refurbishment - UID'S | 12 |  | 2013-01-28 | 12 | nr | bar: PC10 2012-13
KS848 | Newcastle WwTW | 12 |  |  | 12 | nr
KS867 | Copeland Road, Comber, Tank Sewer | 12 |  |  | 12 | nr
KS873 | Bangor DAP Work Package 2: Rathmore Stream UIDs | 12 |  |  | 12 | nr
KS875 | Bangor DAP Works Package 6: Lukes Point WWPS UIDs | 12 |  |  | 12 | nr
KS877 | Bangor DAP Works Package 5 - Clandeboye Stream UIDs | 12 |  |  | 12 | nr
KS878 | Bangor DAP Work Package 7: WWPS - UID'S | 12 |  | 2012-03-28 | 12 | nr | PC10 2011-12: 3
KS879 | Bangor DAP Work Package 4: Bangor Marina UIDs | 12 |  |  | 12 | nr
KS900 | WwPS Upgrades at Groomsport, Killinchy & Craigavad | 12 |  |  | 12 | nr
KS903 | Annalong DAP | 12 |  |  | 12 | nr
KS930 | Millisle DAP Stage 2 Phase 2 | 12 |  |  | 12 | nr
KS937 | Annesborough Park WWPS Upgrade | 12 |  |  | 12 | nr
KS939 | Central Promenade, Newcastle CSO Upgrade (Pattons Bridge) | 12 |  |  | 12 | nr
KS958 | Bangor DAP Works Package 5 Clandeboye Stream UIDs Phase 2 | 12 |  |  | 12 | nr
KT114 | Hillsborough WWTW | 12 |  |  | 12 | nr
KT138 | Beechlawn SPS Hillsborough Upgrade - UID's | 12 |  | 2011-11-30 | 12 | nr | bar: PC10 2011-12
KT139 | River Road SPS Upgrade | 12 |  |  | 12 | nr
KT391 | Lisburn DAP Stage 1 - UID's | 12 |  |  | 12 | nr
KT403 | Drumbeg Drive, Lisburn WWPS Enhancement | 12 |  |  | 12 | nr
KT415 | Glenmore WwPS Lisburn CSO upgrade | 12 |  |  | 12 | nr
KV014 | Castlewellan DAP - UIDs | 12 |  | 2010-08-19 | 12 | nr | PC10 2012-13: 2
KV063 | Newry Rehab | 12 |  | 2011-09-05 | 12 | nr | bar: PC10 2012-13
KV154 | Newry Road SPS Warrenpoint - UID's | 12 |  |  | 12 | nr
KV159 | Water Street/Horners Lane Rostrevor | 12 |  | 2011-06-24 | 12 | nr | bar: PC10 2012-13
KV161 | Castlewellan DAP Stage 1 - UIDs | 12 |  |  | 12 | nr
1821 | Annsborough DA UID-Mill Hill Castlewellan WwPS | 12b |  | 2025-02-20 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1048 | Antrim DA Glenavy Road Crumlin WwPS | 12b |  | 2024-10-16 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1090 | Armagh DA - Storm Tanks | 12b |  | 2026-11-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2332 | Ballymena DA - Dunfane Crescent | 12b |  | 2026-08-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2331 | Ballymena DA - Harryville Bridge CSO | 12b |  | 2026-02-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1829 | Ballymena DAP - Deramore Park CSO | 12b |  | 2026-08-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1857 | Ballymena DAP - Knockan Road CSO | 12b |  | 2026-08-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1904 | Ballymena DAP - N100010347 | 12b |  | 2026-02-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1754 | Ballymena DAP - Spencetown TPS | 12b |  | 2025-09-16 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1796 | Ballymena DAP - The Pentagon CSO | 12b |  | 2026-02-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1891 | Ballymena DAP - Waveney Road Yard CSO | 12b |  | 2026-08-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1673 | Ballymena DAP- Albert Place CSO | 12b |  | 2025-12-16 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2246 | Ballynahinch DA - Loughside Drive WwPS | 12b |  | 2025-12-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1861 | Ballynahinch DA UID-Town CSO | 12b |  | 2025-03-05 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1054 | Ballyrickard DA Upper Crescent Comber WwPS | 12b |  | 2023-02-06 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 4; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1882 | Ballywalter DA UID-Ballywalter Fowler 1 CSO | 12b |  | 2025-01-16 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1878 | Blackcave DA - Solution 1 - Ballygalley Coast Road CSO | 12b |  | 2025-05-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1894 | Blackcave DA - Solution 1 - Ballygalley Slipway WwPS CSO | 12b |  | 2025-05-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1897 | Blackcave DA - Solution 2 - Blackarch East CSO | 12b |  | 2025-05-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2243 | Cookstown DA - Blackhill CSO | 12b |  | 2026-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2242 | Cookstown DA - Burn Bank CSO | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2241 | Cookstown DA - Castle Road CSO | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2244 | Cookstown DA - Coolreaghs Road CSO | 12b |  | 2025-06-03 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2258 | Cookstown DA - Derryloran Industrial Estate One WwPS | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2238 | Cookstown DA - Loran Way CSO | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2239 | Cookstown DA - Orritor Road CSO | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2240 | Cookstown DA - Unipork Molesworth Street CSO | 12b |  | 2026-05-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1062 | Culmore DA - Faughan Crescent WwPS | 12b |  | 2023-04-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1929 | Downpatrick DAP - Ardenlee PS | 12b |  | 2026-03-30 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1930 | Downpatrick DAP - Ardfern PS | 12b |  | 2026-03-30 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1982 | Downpatrick DAP - Down Council Strangford Road CSO | 12b |  | 2026-03-30 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1928 | Downpatrick DAP - Strangford Road PS | 12b |  | 2026-03-30 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2222 | Dromore DAP- Dromore Central PS10 WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2219 | Dromore DAP- Dromore Central WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2221 | Dromore DAP- Invert Siphon CSO | 12b |  | 2026-09-07 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2223 | Dromore DAP- Lower Mount CSO | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2220 | Dromore DAP- PS14 at Invert Siphon Site | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2204 | Dungannon DA - Woodlawn Park CSO | 12b |  | 2025-01-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2529 | Dungannon DAP - Coolhill North WWPS | 12b |  | 2027-01-18 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1842 | Enniskillen DA - Derrychara Link CSO | 12b |  | 2025-03-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1839 | Enniskillen DA - Loughview Drive CSO | 12b |  | 2025-03-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2580 | Enniskillen DA - Rossory One WwPS | 12b |  | 2025-03-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1871 | Enniskillen DA-Riverview Enniskillen WwPS | 12b |  | 2025-03-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2537 | Kilkeel DA - Derryogue Park CSO | 12b |  | 2025-12-11 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2540 | Kilkeel DA - Kilkeel WwTW Stormtanks | 12b |  | 2025-12-11 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2538 | Kilkeel DA - Military Rd WWPS, Corick Way and Kittys Rd CSO | 12b |  | 2025-12-11 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 3; PC21 2026-27: 0
2539 | Kilkeel DA - Rooney Road CSO Uncharted | 12b |  | 2025-12-11 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2545 | Killinchy DA - Inisharoan PS | 12b |  | 2026-09-15 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2600 | Kircubbin DA Cooks Cove WwPS | 12b |  | 2023-03-23 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1154 | Limavady Catchment Upgrades | 12b |  | 2024-03-25 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1143 | Limavady DA - Bovally WwPS | 12b |  | 2024-03-25 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1873 | Limavady DA UID-Ballyclose Street CSO | 12b |  | 2024-03-25 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1865 | Maghera DA UID-Largantogher Park CSO | 12b |  | 2026-07-13 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1764 | Magherafelt DAP - Hospital Road East WwPS (ballyheafer) | 12b |  | 2026-04-09 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1768 | Magherafelt DAP Mill View PS | 12b |  | 2026-04-09 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1459 | Newry DA Newpoint Greenbank TPS | 12b |  | 2026-01-05 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1588 | Newry DA Warrenpoint Rd Two WwPS | 12b |  | 2025-01-09 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2548 | Newtownbreda DA - Option B - Mill Road West CSO | 12b |  | 2024-09-04 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2213 | Newtownbreda DA- Option B Knockbreckan CSO | 12b |  | 2024-09-04 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1152 | North Coast DA Ballycairn CSO CAI Playing Fields KC467 | 12b |  | 2023-03-24 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1094 | North Coast DA Strand Road WwPS | 12b |  | 2023-03-24 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 2; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2520 | North Down DA - KS873 Rathmore Stream UID | 12b |  | 2023-06-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1137 | Portadown DAP Annagh WwPS | 12b |  | 2027-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 4
1910 | Portaferry DAP - Portaferry No 1 PS (North) | 12b |  | 2026-05-08 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
KG183 | Portadown Drainage Area Network Improvements - Meadow Lane and Bann Street | 12b |  | 2023-04-05 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 6; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS872 | Bangor DAP Work Package 1: Carnalea Stream UID | 12b |  | 2021-10-29 | 12 | Nr | PC21 2021-22: 1; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS872 | UID012 KillaneyWWPS 3 | 12 |  | 2018-06-04 | 12 | Nr | PC15 2018-19: 1; PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS872 | UID177 Killaire WWPS 1 | 12 |  | 2016-03-31 | 12 | Nr | PC15 2015-16: 1; PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS874 | Bangor DAP Works Package 3 - Belfast Lough UIDs | 12b |  | 2022-03-29 | 12 | Nr | PC21 2021-22: 3; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS902 | Dundrum DAP, UIDs Upgrades. | 12b |  | 2022-03-31 | 12 | Nr | PC21 2021-22: 3; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1239 | Belfast DA- Forfar Street CSO WwPS | 12b |  | 2027-03-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1240 | Belfast DA- Donegall Place Royal Avenue CSO Sewerage | 12b |  | 2027-03-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1241 | Belfast DA- Shore Road York CSO WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1292 | Belfast DA- Dunlambert Park CSO | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1308 | Belfast DA- North Howard Street CSO WwPS | 12b |  | 2026-06-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1328 | Belfast DA- Shankill Road Lanark CSO WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1353 | Belfast DA Upper Falls Boucher CSO DO45 | 12b |  | 2026-03-05 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1376 | Belfast DA Oldpark Road CSO DO42 | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1507 | Kinnegar DA- Brooklands Ave No.21 Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1509 | Kinnegar DA- Brooklands Crescent WwPS | 12b |  | 2026-05-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1521 | Kinnegar DA- Clara Way Sewage | 12b |  | 2026-05-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1522 | Kinnegar DA- Comber Road Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1523 | Kinnegar DA- Comber Road WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1527 | Kinnegar DA- Cumberland Road Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1530 | Kinnegar DA- Grand Prix Park Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1547 | Kinnegar DA- Holywood Rd No.2 Sewerage | 12b |  | 2024-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1549 | Kinnegar DA- Knock Road | 12b |  | 2026-05-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1553 | Kinnegar DA- Knock Road Playing Fields Sewerage | 12b |  | 2026-05-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1559 | Kinnegar DA- Knocknagoney Country Park Sewerage | 12b |  | 2024-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1573 | Kinnegar DA- Millars Lane SPS Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1575 | Kinnegar DA- Moat Park/ Upper Newtonards Road Sewerage | 12b |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1576 | Kinnegar DA- Orangefield Ave/ Sandhill Parade | 12b |  | 2026-06-25 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1579 | Kinnegar DA- Palmerston Rd/ Holywood Rd Sewerage | 12b |  | 2026-06-25 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1581 | Kinnegar DA- Parkway WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1604 | Kinnegar DA- Sandown Road No. 149 Sewerage | 12b |  | 2026-05-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1605 | Sydenham WwPS | 12b |  | 2027-01-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1780 | Kinnegar DA - Glen Brae WwPS | 12b |  | 2023-08-29 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1789 | Carrick DA - Solution 1 - West Park WwPS | 12b |  | 2026-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1949 | Carrick DA - Solution 2 - Marine Highway Carpark Offline Storage | 12b |  | 2027-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 5
1964 | Kinnegar DA- Abbey Park WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1970 | Kinnegar DA- Kensington Road WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1974 | Kinnegar DA- Knocknagoney Dale WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1979 | Carrick DA - Marine Highway CSO Screen | 12b |  | 2026-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1987 | Carrick DA - Solution 3 - Irish Quarter South CSO | 12b |  | 2027-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
2021 | Kinnegar Da- Knocknagoney Drive WwPS | 12b |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1916 | Carrick DA - Solution 4 - WwTW Boundary CSO Storage Tank | 16a |  | 2025-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1920 | Carrick DA - Solution 4 - WwTW Storm Tanks Overflow | 16a |  | 2025-02-01 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2077 | Belfast DA - Ravenhill Road Ravensdene CSo WwPS | 12b |  | 2026-11-02 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
Wastewater Pumping Stations (Capacity Increase)
1066 | Antrim DA Neillsbrook WwPS | 12c |  | 2024-02-19 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2599 | Ballymagorry DA Ballymagorry Tyrone WwPS | 12c |  | 2023-08-16 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1092 | Bangor DA Ballyrobert Bangor WwPS | 12c |  | 2022-04-08 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1059 | Derryhale DA - Brompton Park WwPS | 12c |  | 2024-03-29 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1079 | Derryhale DA Dobbin WwPS | 12c |  | 2022-10-05 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2526 | Donaghadee DA - Cotton WWPS | 12c |  | 2024-03-19 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1065 | Donnybrewer DA Eglinton Cottage Way WwPS | 12c |  | 2023-04-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1053 | Keady Armagh DA Annvale WwPS | 12c |  | 2023-03-24 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1056 | Moira DA Waringfield WwPS | 12c |  | 2023-12-12 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
2611 | Moy DA Keenaghan WwPS Upgrade | 12c |  | 2023-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1072 | Rathfriland Drumlough DA Sleepy Valley Rathfriland WwPS | 12c |  | 2023-02-28 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1064 | Tamnamore DA Clonmore Road Clontyclay WwPS | 12c |  | 2022-12-27 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1746 | New Growth LWWP | 12c |  | 2027-03-31 | 12 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
Wastewater Treatment Works
KT102 | Dunmurry WwTW Modifications | 16 |  | 2012-03-19 | 13 | nr | bar: PC10 2011-12
KB436 | Whitehead, Ballystruder & Ballycarry Rationalisation | 16 |  | 2012-02-16 | 13 | nr | bar: PC10 2011-12
KR389 | Ballyhalbert WwTW Interim Solution | 16 |  | 2013-03-28 | 13 | nr | bar: PC10 2012-13
KA195 | Mullaghboy WWTW | 16 |  | 2011-04-04 | 13 | nr | bar: PC10 2011-12
KR391 | Portavogie WwTW Interim Solution | 16 |  | 2012-09-24 | 13 | nr | bar: PC10 2012-13
KS253 | Drumaness WwTW | 16 |  | 2010-08-31 | 13 | nr | bar: PC10 2010-11
KB282 | Magherafelt WwTW | 16 |  | 2011-03-28 | 13 | nr | bar: PC10 2010-11
KT125 | Hook's Corner WwTW | 16 |  | 2011-03-28 | 13 | nr | bar: PC10 2010-11
KL393 | Ballymonie WwTW | 16 |  | 2011-03-18 | 13 | nr | bar: PC10 2010-11
KB269 | Toome (Creagh) Sewerage Scheme | 16 |  | 2011-03-22 | 13 | nr | bar: PC10 2010-11
KS307 | Loughries WWTW | 16 |  | 2011-01-25 | 13 | nr | bar: PC10 2010-11
KB281 | Maghera WwTW | 16 |  | 2011-02-03 | 13 | nr | bar: PC10 2010-11
KL363 | Feeny WwTW | 16 |  | 2011-11-25 | 13 | nr | bar: PC10 2011-12
KR310 | Newtownbreda WwTW | 16 |  | 2011-02-04 | 13 | nr | bar: PC10 2010-11
KG145 | Derrytrasna WwTW Upgrade | 16 |  | 2010-11-29 | 13 | nr | bar: PC10 2010-11
KB333 | Cargan WwTW | 16 |  | 2010-11-30 | 13 | nr | bar: PC10 2010-11
KC284 | Cloughmills WwTW | 16 |  | 2010-11-30 | 13 | nr | bar: PC10 2010-11
KB322 | Martinstown WwTW | 16 |  | 2010-12-13 | 13 | nr | bar: PC10 2010-11
KF005 | Coalisland WwTW | 16 |  | 2010-12-01 | 13 | nr | bar: PC10 2010-11
KC299 | Bushmills + Portballintrae WwTW | 16 |  | 2010-12-06 | 13 | nr | bar: PC10 2010-11
KB279 | Stewartstown WwTW Improvements | 16 |  | 2010-11-10 | 13 | nr | bar: PC10 2010-11
KB284 | Coagh WwTW Improvements | 16 |  | 2010-11-10 | 13 | nr | bar: PC10 2010-11
KL300 | Dungiven WwTW | 16 |  | 2010-11-10 | 13 | nr | bar: PC10 2010-11
KV064 | Lurganare WwTW | 16 |  | 2010-09-30 | 13 | nr | bar: PC10 2010-11
KN533 | Rousky Sewerage Scheme | 16 |  | 2010-09-09 | 13 | nr | PC10 2010-11: 1; PC15 2014-15: 0
KB278 | Moneymore STW Imps | 16 |  | 2010-08-18 | 13 | nr | bar: PC10 2010-11
KS224 | Downpatrick WwTW | 16 |  | 2009-12-14 | 13 | nr | bar: PC10 2010-11
KF319 | Annaghmore WwTWs | 16 |  | 2010-09-27 | 13 | nr | bar: PC10 2010-11
KS225 | Ardglass WWTW | 16 |  | 2015-03-20 | 13 | nr | bar: PC15 2014-15
KT377 | New Holland WwTW | 16 |  | 2011-03-28 | 13 | nr | bar: PC10 2010-11
KS374 | Darragh Cross WwTW | 16 |  | 2010-09-07 | 13 | nr | bar: PC10 2010-11
KC338 | Causeway/Aird (New Pumping Station) | 16 |  | 2011-08-23 | 13 | nr | bar: PC10 2011-12
KC416 | Glenstall WwTW - Nutrient Reduction | 16 |  | 2013-02-25 | 13 | nr | bar: PC10 2012-13
KN622 | Omagh WwTW - Nutrient Reduction | 16 |  | 2013-02-25 | 13 | nr | bar: PC10 2012-13
KL465 | Limavady WwTW - Nutrient Reduction | 16 |  | 2013-02-25 | 13 | nr | bar: PC10 2012-13
KF329 | Ardress WWPS Upgrade | 16 |  | 2012-03-31 | 13 | nr | bar: PC10 2011-12
KS857 | Glassdrumman WWTW | 16 |  | 2011-12-23 | 13 | nr | bar: PC10 2011-12
KS216 | Dunmore Sewerage - EC Compliance | 16 |  | 2011-06-30 | 13 | nr | bar: PC10 2011-12
KF320 | Bush WwTW | 16 |  | 2010-06-03 | 13 | nr | bar: PC10 2010-11
KF028 | Keady Wwtw | 16 |  | 2012-11-29 | 13 | nr | bar: PC10 2012-13
KL482 | Tamnaherin Wwtw | 16 |  | 2013-01-28 | 13 | nr | bar: PC10 2012-13
KV105 | Newry WwTW Extension Phase 1 | 16 |  | 2013-01-28 | 13 | nr | bar: PC10 2012-13
KF060 | Brockagh Terrace/Mountjoy WtWT | 16 |  | 2012-08-13 | 13 | nr | bar: PC10 2012-13
KV125 | Forkhill WwTW | 16 |  | 2013-03-28 | 13 | nr | bar: PC10 2012-13
KV045 | Mullaghbane WwTW | 16 |  | 2013-03-28 | 13 | nr | bar: PC10 2012-13
KB287 | Swatragh WwTW | 16 |  | 2013-03-21 | 13 | nr | bar: PC10 2012-13
KB314 | Gulladuff WwTW | 16 |  | 2013-12-16 | 13 | nr | bar: PC13 2013-14
KT114 | Hillsborough WWTW | 16 |  | 2014-03-18 | 13 | nr | bar: PC13 2013-14
KS848 | Newcastle WwTW | 16 |  | 2013-12-09 | 13 | nr | bar: PC13 2013-14
KR501 | Carrickfergus WWTW Upgrade | 16 |  | 2014-03-31 | 13 | nr | bar: PC13 2013-14
KR530 | Belfast WwTW Base Maintenance Phase 2 | 16 |  | 2014-03-18 | 13 | nr | bar: PC13 2013-14
KN631 | Strabane WWTW's Refurbishment | 16 |  | 2013-12-20 | 13 | nr | bar: PC13 2013-14
KL350 | Benone Area Sewerage | 16 |  | 2013-09-16 | 13 | nr
KL350 | Decommission Benone WwTW & construct WwPS | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KL350 | Decommission Drumavelly WwTW & construct WwPS | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KL350 | Decommission Aughil WwTW & construct WwPS | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KL350 | Decommission MoD WwTW & construct WwPS | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KL350 | Decommission NIPS WwTW & construct WwPS | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KL350 | Provision of new Magilligan WwTW | 16 |  | 2013-09-16 | 13 | nr | bar: PC13 2013-14
KP672 | Tempo WwTW | 16 |  | 2015-01-06 | 13 | nr | bar: PC15 2014-15
KS844 | Ballyhornan Outfall - NIEA Enforcement | 16 |  | 2013-12-31 | 13 | nr | bar: PC13 2013-14
KL424 | Magheramason Wwtw | 16 |  | 2015-03-20 | 13 | nr | bar: PC15 2014-15
KR409 | Moneyreagh WwTW (Storm Pumping station) | 16 |  | 2013-12-12 | 13 | nr | bar: PC13 2013-14
KP586 | Clabby Wwtw | 16 |  | 2018-03-30 | 13 | nr | bar: PC15 2018-19
KN599 | Donaghmore Wwtw | 16 |  | 2015-03-19 | 13 | nr | bar: PC15 2014-15
KL487 | Nixon’s Corner | 16 |  | 2015-01-30 | 13 | nr | bar: PC15 2014-15
KL386 | Gortnahey Wwtw | 16 |  | 2014-07-24 | 13 | nr | bar: PC15 2014-15
KS389 | Ballymartin & Blackrock WwTWs | 16 |  |  | 13 | nr
KS389 | Ballymartin WwTW | 16 |  | 2015-03-31 | 13 | nr | bar: PC15 2014-15
KS389 | Blackrock WwTW | 16 |  | 2016-03-31 | 13 | nr | bar: PC15 2016-17
KS355 | Ballynahinch Wwtw | 16 |  | 2014-03-21 | 13 | nr | bar: PC13 2013-14
KS905 | Kilmore & Annacloy WwTW | 16 |  |  | 13 | nr
KS906 | Kilmore WwTW | 16 |  | 2015-03-10 | 13 | nr | bar: PC15 2014-15
KS907 | Annacloy WwTW | 16 |  | 2015-03-11 | 13 | nr | bar: PC15 2014-15
KS887 | Ards South (Ballycranbeg WwTW load reduction) | 16 |  | 2015-03-31 | 13 | nr | bar: PC15 2014-15
KL496 | Feeny WwTW - Replacement Secondary Treatment | 16 |  | 2014-08-08 | 13 | nr | bar: PC15 2014-15
KN596 | Ballymagory WWTW | 16 |  | 2015-03-30 | 13 | nr | bar: PC15 2014-15
KL493 | Artigarvin WwTW | 16 |  | 2015-12-21 | 13 | nr | bar: PC15 2015-16
KN640 | Dromore (Tyrone) WWTW | 16 |  | 2015-03-20 | 13 | nr | bar: PC15 2014-15
KT402 | Dunmurry WWTW Sludge Facility | 16 |  | 2014-03-18 | 13 | nr | bar: PC13 2013-14
KB459 | Maghera WwTW: Phase 2 | 16 |  | 2014-02-04 | 13 | nr | bar: PC13 2013-14
KL394 | Drumsurn Wwtw | 16 |  | 2014-12-16 | 13 | nr | bar: PC15 2014-15
KP668 | Lisnarrick Wwtw | 16 |  | 2014-12-01 | 13 | nr | bar: PC15 2014-15
KT126 | Stoneyford Wwtw | 16 |  | 2014-11-28 | 13 | nr | bar: PC15 2014-15
KI508 | UWWTR MCERT compliance | 16 |  | 2016-01-31 | 13 | nr | bar: PC15 2015-16
KC296 | Ballycastle WwTW | 16 |  | 2017-12-30 | 13 | nr | bar: PC15 2017-18
KN656 | Castle Archdale WwTW | 16 |  | 2016-03-30 | 13 | nr | bar: PC15 2015-16
KG202 | Aghagallon WwTW | 16 |  | 2015-03-31 | 13 | nr | bar: PC15 2014-15
| Waringsford | 16 |  | 2014-09-30 | 13 | nr | bar: PC15 2014-15
KC302 | Ballintoy WwTW | 16 |  | 2020-03-29 | 13 | nr | bar: PC15 2019-20
KS111 | Ards South - Cloughey | 16 |  | 2020-03-31 | 13 | nr | bar: PC15 2018-19
KL489 | Ballykelly WwTW | 16 |  | 2020-03-31 | 13 | nr | bar: PC15 2020-21
| Dundrum WwTW | 16 |  | 2019-03-31 | 13 | nr | bar: PC15 2018-19
KC463 | Ballybogy WwTW | 16 |  | 2021-03-31 | 13 | nr | bar: PC15 2019-20
KA239 | Mullans WwTW (Antrim) | 16 |  | 2018-03-29 | 13 | nr | bar: PC15 2018-19
KF350 | Dungannon WwTW Phase 1 | 16 |  | 2020-03-29 | 13 | nr | bar: PC15 2019-20
KS918 | Greyabbey WwTW | 16 |  | 2020-03-31 | 13 | nr | bar: PC15 2019-20
KG041 | Maghaberry WwTW (additional output in 16/17 draft adjusted outputs submission) | 16 |  | 2019-03-29 | 13 | nr | bar: PC15 2018-19
| The Loup | 16 |  | 2017-03-15 | 13 | nr | bar: PC15 2016-17
KC427 | Ballyvoy | 16 |  | 2021-03-31 | 13 | nr | bar: PC15 2020-21
1660 | Cabragh WwTW | 16a |  | 2026-06-19 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1038 | Grange (Taylorstown) WwTW | 16a |  | 2026-03-30 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1473 | Monea WwTW | 16a |  | 2024-04-09 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
2051 | Dromara WwTW | 16a |  | 2026-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1045 | Drumaness WwTW | 16a |  | 2023-06-23 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1343 | Ballygawley WwTW | 16a |  | 2024-06-21 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1175 | Dromore WwTW | 16a |  | 2026-09-25 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1129 | Mountfield PC21 | 16a |  | 2024-03-22 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1306 | Robinsonstown WwTW | 16a |  | 2025-09-19 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1290 | Tamlaght WwTW | 16a |  | 2024-03-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1525 | Culmore WwTW- Cat 5 | 16a |  | 2026-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1194 | Larne WwTW | 16a |  | 2026-12-18 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1381 | Aghanloo WwTW | 16a |  | 2023-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1096 | Moy WwTW | 16a |  | 2027-03-12 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1209 | Killygonlan WwTW | 16a |  | 2026-03-31 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1354 | Derrycrin WwTW | 16a |  | 2023-06-23 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1358 | Ballyronan WwTW | 16a |  | 2024-03-22 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1070 | Warrenpoint WwTW Phase 2 | 16a |  | 2023-03-17 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1424 | Cat 5- Lisnaskea 2 WwTW | 16a |  | 2024-03-22 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1431 | Stewartstown WwTW | 16a |  | 2023-12-29 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1338 | Pomeroy WwTW | 16a |  | 2023-09-29 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1534 | Markethill WwTW | 16a |  | 2025-03-21 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 0; PC21 2026-27: 0
1583 | Clogher WWTW | 16a |  | 2026-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1246 | Kilkeel WwTW | 16a |  | 2024-03-29 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1222 | Downpatrick WwTW | 16a |  | 2026-12-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1470 | Waringstown WwTW | 16a |  | 2023-12-22 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1226 | Killinchy WwTW | 16a |  | 2026-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1141 | Dungannon WwTW | 16a |  | 2026-06-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1391 | Lough Macrory WwTW | 16a |  | 2023-06-16 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1192 | Newcastle WwTW | 16a |  | 2026-09-29 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1395 | Loughries WwTW | 16a |  | 2023-03-21 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1191 | Newry WwTW | 16a |  | 2027-03-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1993 | Dundrum WWTW | 16a |  | 2025-09-26 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
2202 | Bellaghy WwTW | 16a |  | 2026-03-17 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1196 | Annsborough WwTW | 16a |  | 2025-06-27 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1169 | Meigh WwTW | 16a |  | 2023-06-23 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1339 | Kilrea WwTW | 16a |  | 2024-03-22 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS113 | Ards North, Carrowdore, Ballywalter, Ballyhaskin | 16 |  | 2024-03-31 |  |  | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS113 | Carrowdore WwTW | 16a |  | 2023-03-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS113 | Ballywalter WwTW | 16a |  | 2023-03-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS113 | Ballyhaskin WwTW | 16a |  | 2023-03-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 1; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS235 | Ballygowan WwTW | 16 |  | 2022-03-31 |  |  | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS235 | Ballygowan WwTW | 16a |  | 2023-05-15 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
KS235 | Moneyreagh WwTW | 16 |  | 2019-03-31 | 13 | Nr | PC15 2018-19: 1; PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1594 | Whitehouse WwTW | 16b |  | 2024-03-07 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 1; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 0
1652 | Belfast WwTW - Phase 1 upgrade | 16b |  | 2027-02-10 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1702 | Greenisland WwTW | 16b |  | 2026-01-13 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 1; PC21 2026-27: 0
1800 | Carrickfergus WwTW | 16b |  | 2026-07-06 | 13 | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
Small Wastewater Treatment Works
KI486 | Annahugh WwTW | 17 |  | 2010/2011 | 13 | nr | bar: PC10 2010-11
KI486 | Galbally WwTW | 17 |  | 2010/2011 | 13 | nr | bar: PC10 2010-11
KI486 | Maghery WwTW | 17 |  | 2010/2011 | 13 | nr | bar: PC10 2010-11
KI486 | Montieth WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
KI486 | Orritor WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
KI486 | Garvaghy WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
KI486 | Donagheady WwTW | 17 |  | 2010/2011 | 13 | nr | bar: PC10 2010-11
KI486 | Attical Tullyframe WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
KI486 | Donagh WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
KI486 | Glack WwTW | 17 |  | 2012/2013 | 13 | nr | bar: PC10 2012-13
KI486 | Teemore WwTW | 17 |  | 2011/2012 | 13 | nr | bar: PC10 2011-12
| Small Wastewater Treatment Works - PC10 Programme <250pe to be detailed | 17 |  | 2010-2013 | 14 | nr | PC10 2010-11: 11; PC10 2011-12: 23; PC10 2012-13: 14
| Small Wastewater Treatment Works - PC13 Programme <250pe to be detailed | 17 |  | 2013-2015 | 14 | nr | PC13 2013-14: 7; PC15 2014-15: 18
| Small Wastewater Treatment Works - PC15 Programme <250pe to be detailed | 17 |  | 2015-2021 | 14 | nr | PC15 2015-16: 4; PC15 2016-17: 8; PC15 2017-18: 3; PC15 2018-19: 8; PC15 2019-20: 10; PC15 2020-21: 11
1198 | RWwIP RBC <50PE (Current PE) | 17z |  | 2027-03-30 | 14 | Nr | PC21 2021-22: 6; PC21 2022-23: 6; PC21 2023-24: 6; PC21 2024-25: 6; PC21 2025-26: 6; PC21 2026-27: 6
Small Wastewater Treatment Works (Sustainable Solutions)
2577 | RWWIP – Sustainable Option | 17z |  | 2027-03-30 |  | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 1; PC21 2025-26: 1; PC21 2026-27: 1
Wastewater Siphons
1130 | Culmore DA Strathfoyle Siphons | 12i |  | 2027-01-31 |  | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
1127 | Belfast DA Queens Bridge Siphons | 12H |  | 2026-05-13 |  | Nr | PC21 2021-22: 0; PC21 2022-23: 0; PC21 2023-24: 0; PC21 2024-25: 0; PC21 2025-26: 0; PC21 2026-27: 1
Event Duration Monitors
1323 | Event Duration Monitors WwPS/CSOs | 12b |  | 2027-03-30 |  | Nr | PC21 2021-22: 50; PC21 2022-23: 50; PC21 2023-24: 100; PC21 2024-25: 150; PC21 2025-26: 150; PC21 2026-27: 146
1469 | Event Duration Monitors WwTW | 16d |  | 2027-03-31 |  | Nr | PC21 2021-22: 16; PC21 2022-23: 17; PC21 2023-24: 17; PC21 2024-25: 16; PC21 2025-26: 16; PC21 2026-27: 16
BP T4.1 | Water Outputs | [5 empty] | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
19 | Completion of nominated trunk main schemes |  |  |  | 6 |  | 2 | 0 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 5 | 2 | 4
20 | Completion of nominated water treatment works schemes |  |  |  | 7 |  | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 6 | 4 | 1 | 7
21 | Completion of nominated improvements to increase the capacity of service reservoirs and clear water tanks |  |  |  | 8 |  | 5 | 3 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 0
BP T4.2 | Sewerage Outputs | [5 empty] | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
8 | Delivery of improvements to nominated UIDs as part of a defined programme of work |  |  |  | 12 |  | 20 | 43 | 38 | 28 | 39 | 26 | 11 | 11 | 8 | 3 | 3 | 7 | 21 | 21 | 13 | 25 | 49
9 | Delivery of improvements to nominated WwTWs as part of a defined programme of work |  |  |  | 13 |  | 29 | 14 | 13 | 17 | 18 | 3 | 2 | 1 | 6 | 4 | 2 | 0 | 5 | 16 | 3 | 7 | 14
10 | Small wastewater treatment works delivered as part of the rural wastewater investment programme |  |  |  | 14 |  | 11 | 23 | 14 | 7 | 18 | 4 | 8 | 3 | 8 | 10 | 11 | 6 | 6 | 6 | 6 | 6 | 6