## Executive Summary

## Twenty-five schemes were run during 2003-4, with a further 2 schemes from the previous year being reported on, representing a total funding of £3,938,905. Total lifetime energy savings are estimated at 449 GWh, with 84,614 tonnes carbon savings and £17,221,109 customer energy cost savings over the lifetimes of the measures. Twelve schemes were in the Priority (Fuel Poverty) sector and the remainder were non-Priority domestic and non-domestic.

## While the Levy is open to second tier suppliers, NIE was the only supplier to submit schemes and earned incentive payments, for exceeding the energy savings target, of ca £360,000, in line with expectations.

## The terms of the new framework document were not fully implemented due to certain schemes following on from the previous year, which was also not subject to the new terms due to delays in finalising the new framework document. However, improvements were made in terms of reporting on Quality Monitoring and Customer Satisfaction feedback.

## In 2004-5 the terms of the new Framework Document are being implemented fully, including the bidding process, with a second tier supplier having successfully submitted a scheme.

Dr Patrick Waterfield on behalf of EST

## Summary of NI Energy Efficiency Customer Levy Schemes 2003-4

1.0 Introduction

  - The 2003-4 period of the Levy was the second following the increase in funding to £5 per customer and the shift from energy efficiency in general to fuel poverty. As recommended by the Assembly, 80% of funding was to be directed towards the fuel poverty sector (priority) with the remaining 20% for non-priority domestic schemes and also non-domestic schemes.

  - The Framework Document identifies dwellings at risk of fuel poverty as those having no central heating or having electric storage heating systems. The term “fuel poverty proofing” was coined, to represent a package of measures - hot water cylinder and fabric (walls and roof) insulation, as well as heating system replacement (fuel switching) and controls - which would be applied to those dwellings at risk of fuel poverty as defined above, accounting for 80% of total funding available.

  - The increase in funding and shift in emphasis has caused the Levy to be seen as an integral element in the fuel poverty abatement strategy for Northern Ireland. Indeed, EAGA, which runs the Warm Homes and Warm Homes Plus schemes, has made it known in the past that they could not operate either scheme without input from the Levy.

  - Around 40% of Levy funds has been directed to EAGA in previous years, which proportion was maintained in 2003-4. However, under the terms of the new Framework Document, this would now apply to Warm Homes Plus only, which provides the package of measures required for Fuel Poverty Proofing of a dwelling. In practice, as detailed below, Levy funding of EAGA in 2003-4 was not directed exclusively to Warm Homes Plus, but also to Warm Homes.

  - The remaining 40% of Priority funding would go on full fuel poverty proofing packages (as described above) and would yield figures of numbers of dwellings “Fuel Poverty Proofed”. The 40% directed to Warm Homes Plus would supplement DSD funding (typically by meeting insulation costs and topping up heating system replacement where the DSD ceiling was insufficient) and would yield figures of numbers of dwellings “Fuel Poverty Proofing Assisted”. Corresponding targets would be set in each case (again, in practice, these targets were not set for 2003-4, due to schemes following on from 2002-3 which had already commenced by the time the Framework Document was agreed).

  - A consultation process had been undertaken prior to the 2002-3 period, with fuel poverty groups and others with vested interests in the Levy, canvassing opinion on how the Levy should be structured and operated. One key recommendation was for greater transparency in the way in which the Levy is set out (in the Framework Document), operated and reported, with particular emphasis on the need for robust quality systems.

  - To this end: the scheme submission spreadsheet was extensively modified; Quality Monitoring and Customer Satisfaction proposals and feedback were specifically requested as part of submission documentation; and reporting was extended to provide more useful data, especially regarding fuel poverty proofing. These practices have become established during the 2003-4 period.

  - The Levy was also more explicitly opened up to Second Tier suppliers, with a bidding process introduced, to ensure that the most cost effective schemes were selected to proceed. In practice, in 2003-4, there were no proposals from Second Tier suppliers while, due to the delay in finalising the Framework Document, the bidding process was suspended until the following year.

2.0 Utilisation of Levy Funding

| Ref No. | Scheme Title (P = Priority Group, nP = non-Priority Group) | Lifetime Savings |  |  |
| --- | --- | --- | --- | --- |
|  |  | Energy (GWh) | Carbon (tonnes) | Customer (£) |
| NIE0301M NIE0302A NIE0303A NIE0304L NIE0305M NIE0306M NIE0307M NIE0308M NIE0309M NIE0310M NIE0311M NIE0312M NIE0313L NIE0314A NIE0315A NIE0316A NIE0317M NIE0318O NIE0319A NIE0320L NIE0321L NIE0322O NIE0323O NIE0324L NIE0325M NIE0326M NIE0327O NIE0217H NIE0220O | Craigavon Energy Efficiency (P) Miele Appliance Trade-in (nP) Ariston Appliance Trade-in (nP) EEAC CFL Give-away (nP) No Age to Golden Age Belfast (P) No Age to Golden Age Coleraine (P) No Age to Golden Age Downpatrick (P) No Age to Golden Age Newry (P) Warm Homes (P) Foyle Energy Project (P) Rural Energy Saving Scheme (P) RCN Community Halls (nP) Lighting for Agricultural Premises (nP) Electrolux/CIR Appliance Scheme (nP) Electrolux/Laser Appliance Scheme (nP) Euronics Staff Discount Scheme (nP) Energy Shareholders Club (nP) Radiator Panels - Special Packet (nP) Excelsior Ariston Appliance (nP) Powercell Lighting Scheme (nP) Powercell Ambiance Lighting (nP) Phoenix Gas Interest Free Loan (nP) E7 Replacement (Cosy Homes) (P) Fishing and Farming Antrim and Down Rural Scheme (P) Hard to Heat Homes (P) Microsave Phoenix Gas Boiler (nP) No Age to Golden Age Heating (P) | 8.930 1.655 3.310 6.735 5.940 5.659 4.189 3.115 186.049 20.585 16.187 1.444 11.901 2.014 1.847 2.596 3.728 1.523 0.083 5.003 2.196 56.743 19.720 DID 16.873 0.172 DID 59.322 1.593 | 2,126 372 746 1,878 1,191 952 801 648 20,325 4,803 3,434 423 3,864 454 415 581 1,003 292 19 1,171 443 14,330 4,924 NOT 3,839 34 NOT 15,137 409 | 388,015 148,964 297,934 606,162 398,946 343,779 219,917 225,655 5,286,511 923,725 805,281 67,574 1,071,117 181,297 166,268 233,677 317,908 78,634 7,458 450,256 197,633 1,429,883 794,646 PROCEED 813,402 8,801 PROCEED £1,692,815 £64,851 |
| TOTAL |  | 449.112 | 84,614 | 17,221,109 |

Schemes reported in 2003-4 showing Lifetime Energy, Carbon and Cost Savings

  - The table above shows a summary of schemes implemented and lifetime savings in terms of energy, carbon and customer costs.

  - Though total funding of £3,922,235 available in 2003-4, £3,938,905 was spent on the schemes listed in the table below, representing a minor overspend. This was despite two schemes not progressing, as indicated. Any overspend (or underspend) is not critical as the adjustment can be taken up the following year.

  - As shown, two schemes run in 2002-3 were reported on in 2003-4 - No Age to Golden Age Heating, due to non-availability of information from the scheme (for unforeseeable reasons) and Phoenix Gas Boiler Scheme, due to a decision by NIE to defer reporting, as the target savings for that year had already been well exceeded. The target for 2003-4 was, of course, adjusted to take account of the extra savings arising from the reporting of these previous schemes.

- Target Achievement and Incentive Payments

  - The overall energy saving target for 2002-3 was set at 367.5GWh. As shown on the above table, the actual savings achieved were 449GWh. It is always anticipated that suppliers will exceed the target and thus earn incentive payments (see below).

  - The extent of over-achievement was thus 81.6GWh which, at a level of £4,415 per GWh as given in the Framework Document, yielded NIE (the only supplier involved in this round) incentive payments of some £360,308. This is commensurate with the expected level of incentive payments of ca £350,000, which was based on that received in previous years.

- Extent of Priority Funding

  - It was agreed that, though required in the Framework Document, Fuel Poverty Proofing targets as such would not be set for 2003-4, due to the prior approval of follow-on schemes, as detailed above. Instead, a figure was to be reported on numbers of homes fuel poverty-proofed and numbers assisted in fuel poverty proofing (corresponding, respectively, to full packages of measures implemented under Levy schemes and top-up packages funded under the Levy for Warm Homes Plus).

  - Of the total of £3,938,905 spent on schemes in 2003-4, £3,291,804 was accounted for by Priority Group schemes, representing 83.60%. From the above table, a total of 289.012 GWh was saved in Priority Group measures, representing 64.4% of total savings. Thus it may be seen that while the recommended allocation to the fuel poverty sector was actually exceeded, energy savings were not commensurate with spend for this sector, due in the main to a couple of highly cost effective non-Priority schemes.

- Funding Available and Targets for 2004-5

  - In accordance with the terms of the Framework Document, any underspend/ overspend from one year must be adjusted for the following year. In this case, £16,670 will be deducted from the £3,815,437 to be made available in 2004-5, totalling £3,798,767. Allowing for this minor adjustment and in absence of any subsequent changes, the target for 2004-5 will be around 265 GWh.

# Conclusions

# The 2002-3 Levy period was seen as an interim period between the previous and new Framework Documents. The 2003-4 period has been a continuation of that interim period. Some, though not all, of the requirements of the new Framework were implemented, exceptions being due, directly or indirectly, to the knock-on effects of the previous period and the fact that certain schemes were following on in 2003-4.

# While fuel poverty proofing packages were not implemented in accordance with the new Framework Document and targets for numbers of homes fuel-poverty proofed and assisted were not set, the figures for overall spend indicate a focus on the priority group in accordance with that recommended by the Assembly and written into the Framework Document.

# Submissions received for the year 2004-5 will be evaluated under the new bidding process. The requirement for Fuel Poverty Proofing packages will be implemented fully and numbers of homes fuel-poverty proofed and assisted will be reported. Energy saving and other targets will therefore be set with confidence.

# The recommendation is made that post implementation reports for 2004-5 schemes must be submitted well before the commencement of the submission period for 2006-7.